## implements
Task | Finish | Due date
Friend
Search friends | Yes
Invite friend | Yes
List of friends | Yes
Friend on common | Yes
Track active friends | Yes
Post
Assignment | Yes
Test | Yes
Project | Yes
Exam | Yes
Education | Yes
Tutor | Yes
Book | Yes
Job | Yes
Party | Yes
Student awareness | Yes
Housing | Yes
Team up | Yes
Album
Photo | yes | 2009-03-17
Music | yes | 2009-03-19
Video | yes | 2009-03-21
Inbox
Home | Yes
Inbox | Yes
Profile | Yes
Share a story | yes | 2009-03-24
Search | yes | 2009-03-30
Post more like this | yes | 2009-04-01
Integrate lightboxXL for Photo, Music, Video | yes | 2009-04-04

## UI
Task | Finish
Friend
Search friends | Yes
Invite friend | Yes
List of friends | Yes
Post
Assignment | Yes
Test | Yes
Project | Yes
Exam | Yes
Education | Yes
Tutor | Yes
Book | Yes
Job | Yes
Party | Yes
Student awareness | Yes
Housing | Yes
Team up | Yes
Album
Photo | No
Music | No
Video | No
Inbox
Home | Yes
Inbox | No
Profile | No
Share a story | No
message box | No